# HRMS AI Chatbot — Complete Implementation Specification

Version: 1.0 Date: April 2026 Status: Ready for Development Project Duration: 4 weeks (full-time) Difficulty Level: ⭐⭐⭐⭐ (Medium-Hard)

## Table of Contents

- Executive Summary

- System Architecture

- Correct Implementation Order (Phases)

- Phase 1: Action Handler Foundation

- Phase 2: SQL Intelligence

- Phase 3: Multi-Step Planner + Docs/RAG

- Phase 4: Calendar & Email Integration

- Database Schema

- Security & RBAC

- API Specifications

- Frontend Components

- Testing Strategy

- Deployment & Rollout

- Risk & Mitigation

## Executive Summary

### What We’re Building

An AI Copilot embedded in your HRMS that lets employees and admins manage their entire workflow through natural language conversation. No more clicking through dashboards — just ask:

- “Check me in”

- “Apply leave for next week”

- “Who’s working on HRMS Backend? Show me progress”

- “Which employees are absent today?”

- “Send a reminder email to all on-leave employees”

- “Schedule a meeting with the AI team”

### Why This Order?

NOT: Email first, then SQL, then docs BUT: Actions → SQL → Multi-Step Planner + Docs → Calendar/Email

Why? Each phase is a foundation for the next:

- Phase 1 (Actions): Basic capability

- Phase 2 (SQL): Query capability

- Phase 3 (Planner + Docs): Orchestration capability (needed before external tools)

- Phase 4 (Calendar/Email): External tool integration (builds on Phase 3)

### Timeline & Effort

| Phase | Week | Duration | Tasks |
| --- | --- | --- | --- |
| 1: Actions | 1 | 5 days | Chat UI, intent classifier, API calls |
| 2: SQL | 2 | 5 days | Query templates, validator, role filtering |
| 3: Planner+Docs | 3 | 7 days | Multi-step orchestrator, RAG pipeline |
| 4: Calendar/Email | 4 | 5 days | Gmail/SMTP, Google Calendar, integrations |
| Total | 4 weeks | 22 days |  |

### Key Metrics for Success

- ✅ Phase 1 done: Users can check-in/out, apply leave, view balance via chat

- ✅ Phase 2 done: Admins can query team data in plain English

- ✅ Phase 3 done: Multi-step workflows work (“show team + progress”, pending approvals with policy)

- ✅ Phase 4 done: Email campaigns and calendar scheduling work end-to-end

## System Architecture

### Core Components

┌─────────────────────────────────────────────────────────────┐
│                     User (Web Chat UI)                      │
└────────────────────────┬────────────────────────────────────┘
                         │
                         ↓ POST /ai/chat
┌─────────────────────────────────────────────────────────────┐
│                    FastAPI Router                           │
│  ├─ Intent Classifier (ACTION|SQL|DOCS|MULTI_STEP)          │
│  └─ User Context Injector (role, status, permissions)       │
└────────────────────────┬────────────────────────────────────┘
                         │
         ┌───────────────┼───────────────┬──────────────┐
         ↓               ↓               ↓              ↓
    ┌────────┐    ┌──────────┐    ┌──────────┐  ┌─────────────┐
    │ Action │    │   SQL    │    │ Docs/RAG │  │ Multi-Step  │
    │Handler │    │ Handler  │    │ Handler  │  │ Orchestrator│
    └────┬───┘    └────┬─────┘    └────┬─────┘  └──────┬──────┘
         │             │               │               │
         ↓             ↓               ↓               ↓
    Your Existing   PostgreSQL    pgvector       Combines all
    REST APIs       (SELECT only)  (embeddings)   handlers
         │             │               │               │
         └───────────────────────────────────────────────┘
                         │
                    ↓ Formatted
              Natural Language
                  Response
                         │
                 Chat UI (React)

### Data Flow for “Show team progress on HRMS Backend”

User: "Who's working on HRMS Backend? Show progress"
  ↓
Router classifies as MULTI_STEP
  ↓
Planner thinks: I need (1) team list (2) their tasks (3) combine
  ↓
Step 1: SQL Handler
  Query: SELECT employee FROM project_assignments WHERE project='HRMS Backend'
  Result: [Yash, Shlok, Saif]
  Chat: "Found 3 team members..."
  ↓
Step 2: Action Handler Loop
  For Yash: GET /tasks?emp=Yash → 4 done, 4 pending
  For Shlok: GET /tasks?emp=Shlok → 6 done, 2 pending
  For Saif: GET /tasks?emp=Saif → 2 done, 6 pending
  Chat: Shows progress as it loads
  ↓
Step 3: LLM Summarize
  "Team is 50% done. Shlok leading (75%), Yash at 50%, Saif at 25%"
  ↓
Step 4: Format + Display
  Table in chat with names, progress bars, status

## Correct Implementation Order (Phases)

### Why This Order Matters

Dependency Chain:

- Phase 1 is foundation (nothing depends on it being done)

- Phase 2 depends on Phase 1 (role checking from Phase 1)

- Phase 3 depends on Phases 1+2 (combines actions + SQL)

- Phase 4 depends on Phase 3 (uses planner to orchestrate email/calendar)

Build it wrong order (email first):

- Email handler tries to query employees

- SQL doesn’t exist yet

- Sends to EVERYONE (disaster)

Build in correct order:

- Phase 1: Actions work

- Phase 2: SQL works (can now query employees safely)

- Phase 3: Planner works (can now combine actions + SQL)

- Phase 4: Email works (built on proven Phase 3 foundation)

## Phase 1: Action Handler Foundation

Duration: 5 days Difficulty: (Medium) Deliverable: Chat box where users can “Check me in”, apply leave, view balance

### What Gets Built

#### 1.1 Chat UI (React Component)

- Floating button (bottom-right corner)

- Slide-in chat panel with:

  - Message list (user + assistant)

  - Input field with send button

  - Quick action chips (role-based suggestions)

  - Loading spinner during API calls

- Persistence in localStorage (chat history survives page reload)

#### 1.2 Intent Classifier

Simple LLM prompt that classifies user message into one of:

- ACTION — “Check me in”, “Apply leave”, “Show my tasks”

- SQL — “Who is absent?”, “Show attendance”

- DOCS — “What is leave policy?”, “How many leaves?”

- MULTI_STEP — Complex multi-part queries

- CHAT — “Hi”, “How does this work?”

- AMBIGUOUS — Needs clarification

Returns: { intent: "ACTION", confidence: 0.91 }

#### 1.3 User Context Builder

Gathers user data once per message:

{
  user_id: "emp_123",
  name: "Yash",
  email: "yash@company.com",
  role: "admin",
  department: "AI Engineering",
  checked_in_today: true,
  checked_in_at: "09:30 AM",
  leave_balance: {
    casual: 8,
    sick: 5,
    comp_off: 2
  },
  active_projects: ["HRMS Backend", "E-Commerce"],
  current_time: "10:45 AM",
  organization_id: "org_1"
}

This is injected into every LLM call as system context, so AI always knows who the user is without needing to “look it up.”

#### 1.4 Action Handler

Maps natural language to API calls:

| User Says | API Called | Role Required |
| --- | --- | --- |
| “Check me in” | POST /attendance/check-in | employee, admin |
| “Check me out” | POST /attendance/check-out | employee, admin |
| “Apply leave tomorrow” | POST /requests (type:leave) | employee, admin |
| “Show my leaves” | GET /balance/me | employee, admin |
| “My tasks today” | GET /tasks/today | employee, admin |
| “Approve Shlok’s leave” | POST /requests/{id}/approve | admin only |
| “Add employee: saif@co.com” | POST /employee/add | admin only |

Key rule: Never call API directly. Always:

- Extract parameters (LLM helps)

- Check RBAC (user has permission?)

- Call your existing API

- Format response naturally

- Log to audit_log

#### 1.5 Database Tables

-- Conversation history
CREATE TABLE ai_conversations (
  id UUID PRIMARY KEY,
  employee_id UUID REFERENCES employees(id),
  role VARCHAR(10), -- 'user' or 'assistant'
  content TEXT,
  created_at TIMESTAMP,
  turn_number INT -- which turn in conversation
);

-- Every AI action logged
CREATE TABLE ai_audit_log (
  id UUID PRIMARY KEY,
  employee_id UUID REFERENCES employees(id),
  intent_type VARCHAR(50), -- ACTION, SQL, etc
  action_taken VARCHAR(255), -- "checked_in", "applied_leave", etc
  api_called VARCHAR(255), -- "/attendance/check-in"
  parameters JSONB, -- what was passed
  result VARCHAR(50), -- 'success', 'failed', 'error'
  error_message TEXT,
  llm_confidence FLOAT,
  created_at TIMESTAMP
);

#### 1.6 POST /ai/chat Endpoint

Request:
  POST /ai/chat
  {
    message: "Check me in",
    conversation_history: [
      { role: "user", content: "Hello" },
      { role: "assistant", content: "Hi! How can I help?" }
    ]
  }
  Headers: Authorization: Bearer {jwt_token}

Response:
  {
    status: "success",
    intent: "ACTION",
    action: "check_in",
    response: "Checked you in at 09:45 AM. Have a great day!",
    api_call: "POST /attendance/check-in",
    conversation_id: "conv_123"
  }

### Testing Checklist for Phase 1

- ☐ Chat UI opens and closes smoothly

- ☐ Intent classifier correctly identifies at least 10 test messages

- ☐ User context loads correctly (role, name, leave balance)

- ☐ Action handler calls /attendance/check-in and returns success

- ☐ Action handler calls /requests to apply leave

- ☐ RBAC: Employee cannot approve other’s leave

- ☐ RBAC: Admin can approve leave

- ☐ Conversation history persists across page reload

- ☐ Audit log records every action with timestamp + user

- ☐ Error handling: What if API is down? (show friendly message)

### Go/No-Go Criteria for Phase 1

✅ User can: check-in, check-out, apply leave, view balance, my requests, see today’s tasks ✅ All actions are logged to audit_log ✅ Permissions enforced (no privilege escalation) ✅ Chat works on desktop + mobile

## Phase 2: SQL Intelligence

Duration: 5 days Difficulty: (Medium-Hard) Deliverable: “Who was absent today?” works, “Show project summary” works

### Why SQL is Phase 2 (Not Free LLM SQL)

Wrong approach: Let LLM write SQL freely

- Could query sensitive tables

- Could be slow (no LIMIT, GROUP BY bombs)

- Could access data user shouldn’t see

- Inconsistent output format

Right approach: Template-based SQL

- You write 10-15 safe SQL queries once

- LLM only extracts parameters

- All queries are tested + optimized

- Responses are consistent

### 2.1 SQL Query Templates

Pre-write these templates. LLM just fills in [PARAM]:

Template 1: Who was absent today?

SELECT e.name, e.email
FROM employees e
WHERE e.id NOT IN (
  SELECT DISTINCT employee_id FROM attendance_sessions
  WHERE DATE(session_start) = CURRENT_DATE
)
AND e.is_active = true
AND e.organization_id = '[ORG_ID]'
ORDER BY e.name
LIMIT 100;

Template 2: Average hours this month

SELECT 
  e.name,
  ROUND(AVG(EXTRACT(EPOCH FROM (s.session_end - s.session_start))/3600), 2) as avg_hours
FROM employees e
JOIN attendance_sessions s ON e.id = s.employee_id
WHERE DATE_TRUNC('month', s.session_start) = DATE_TRUNC('month', CURRENT_DATE)
AND e.organization_id = '[ORG_ID]'
AND (e.id = '[EMPLOYEE_ID]' OR '[ROLE]' = 'admin') -- RBAC filter
GROUP BY e.id, e.name
ORDER BY avg_hours DESC
LIMIT 100;

Template 3: Pending requests count

SELECT 
  request_type,
  COUNT(*) as count
FROM requests
WHERE status = 'pending'
AND organization_id = '[ORG_ID]'
AND (requested_by = '[EMPLOYEE_ID]' OR '[ROLE]' = 'admin')
GROUP BY request_type
ORDER BY count DESC;

Template 4: Project hours logged

SELECT 
  p.name,
  ROUND(SUM(EXTRACT(EPOCH FROM (t.end_time - t.start_time))/3600), 2) as hours
FROM projects p
LEFT JOIN tasks t ON p.id = t.project_id
WHERE p.organization_id = '[ORG_ID]'
GROUP BY p.id, p.name
ORDER BY hours DESC
LIMIT 100;

Template 5: Who is working on project X

SELECT DISTINCT e.name, e.email
FROM employees e
JOIN project_assignments pa ON e.id = pa.employee_id
JOIN projects p ON pa.project_id = p.id
WHERE p.name = '[PROJECT_NAME]'
AND e.is_active = true
AND e.organization_id = '[ORG_ID]'
ORDER BY e.name
LIMIT 100;

(Write 10-15 total templates)

### 2.2 SQL Validator

Before executing ANY query:

1. Check table name is in whitelist:
   ✅ employees, attendance_sessions, requests, projects, tasks, leaves
   ❌ users, passwords, payroll, anything else
2. Check for SELECT-only:
   ❌ INSERT, UPDATE, DELETE, DROP
   ✅ SELECT only
3. Check for LIMIT:
   ❌ SELECT * FROM employees; (no limit)
   ✅ SELECT * FROM employees LIMIT 100;
4. Add parameterized queries (no string interpolation):
   ❌ "SELECT * FROM employees WHERE name = '" + user_input + "'"
   ✅ "SELECT * FROM employees WHERE name = %s", [user_input]
5. Add 5-second timeout:
   ❌ Runaway queries that hang system
   ✅ Kill if takes > 5 seconds

### 2.3 Parameter Extraction

LLM extracts parameters from natural language:

User: "Show me absent employees from last week"

LLM extracts:
{
  template: "who_was_absent",
  parameters: {
    date: "2026-04-17", -- last week
    organization_id: "org_1",
    employee_id: "emp_123",
    role: "admin"
  }
}

Validator runs:
SELECT ... WHERE DATE(session_start) = '2026-04-17' LIMIT 100;

### 2.4 Role-Based Filtering

Employee queries: Automatically filtered to own data

WHERE employee_id = '[CURRENT_EMPLOYEE_ID]'

Admin queries: Full org data

WHERE organization_id = '[ORG_ID]'

Template system builds this in automatically.

### 2.5 Response Formatting

Raw SQL result → Natural language:

SQL Result:
[
  { name: "Saif", email: "saif@..." },
  { name: "Shlok", email: "shlok@..." },
  { name: "Yash", email: "yash@..." }
]

LLM formats as:
"3 employees were absent today: Saif (DevOps), Shlok (Backend), Yash (AI). All have been marked absent in the system."

### Testing for Phase 2

- ☐ Template 1 (absent today): Returns correct list

- ☐ Template 2 (avg hours): Calculations correct

- ☐ Template 3 (pending requests): Counts match

- ☐ Template 4 (project hours): Sums correct

- ☐ Template 5 (project team): Lists correct members

- ☐ Validator blocks unwhitelisted tables

- ☐ Validator blocks UPDATE/DELETE

- ☐ Queries timeout after 5 seconds

- ☐ Employee can only see their own data

- ☐ Admin sees all data

- ☐ All queries logged with user + timestamp

### Go/No-Go for Phase 2

✅ “Who was absent yesterday?” returns correct names ✅ “Show attendance for April” returns daily breakdown ✅ “Which project has the most hours?” returns project name + hours ✅ Employee cannot see other employee’s leave balance ✅ All queries complete in <1 second

## Phase 3: Multi-Step Planner + Docs/RAG

Duration: 7 days Difficulty: (Hard) Deliverable: “Show team progress”, “Find who needs approval”, “Policy Q&A” all work with multi-step orchestration

### 3.1 Multi-Step Agent Planner

For complex queries that need 2+ steps.

Example: “Who’s working on HRMS Backend? Show me their progress”

Step 1 — Plan:

LLM thinks ahead:
"I need to:
  1. Find employees on HRMS Backend project
  2. Get their tasks and status
  3. Summarize progress percentage"

Step 2 — Execute Step 1 (SQL):

SELECT DISTINCT e.name
FROM employees e
JOIN project_assignments pa ON e.id = pa.employee_id
WHERE pa.project_name = 'HRMS Backend'

Result: [Yash, Shlok, Saif]
Chat shows: "Found 3 team members..."

Step 3 — Execute Step 2 (Loop Actions):

For each employee:
  GET /tasks?emp=Yash
  GET /tasks?emp=Shlok
  GET /tasks?emp=Saif

Results:
  Yash: 4 done, 4 pending (50%)
  Shlok: 6 done, 2 pending (75%)
  Saif: 2 done, 6 pending (25%)

Chat shows: Progress loads as it runs

Step 4 — Summarize:

LLM writes:
"Team is 50% complete on HRMS Backend.
Shlok is leading (75%), Yash is on track (50%), Saif is behind (25%).
Main blockers: Backend API integration (blocking Saif), Database schema changes (blocking Yash)."

Step 5 — Format & Display:

Table in chat:
Name   | Done | Pending | Progress | Status
-------|------|---------|----------|--------
Shlok  | 6    | 2       | 75%      |  On track
Yash   | 4    | 4       | 50%      |  On track
Saif   | 2    | 6       | 25%      |  Behind

### 3.2 Planner Orchestrator Implementation

class MultiStepOrchestrator:
    def plan(self, user_message, context):
        # LLM creates step-by-step plan
        plan = llm.generate(
            f"Create a plan for: {user_message}",
            system="You are a planning expert. Return numbered steps."
        )
        return parse_plan(plan)
  
    def execute(self, plan, context):
        results = []
        for i, step in enumerate(plan.steps):
            # Determine which handler to use
            if step.type == "SQL":
                result = sql_handler.execute(step)
            elif step.type == "ACTION":
                result = action_handler.execute(step)
            elif step.type == "DOCS":
                result = docs_handler.execute(step)
          
            results.append(result)
            # Send progress to chat UI
            send_chat_update(f"Step {i+1}/{len(plan.steps)}: {result}")
      
        return results
  
    def summarize(self, results, context):
        # LLM combines all results
        summary = llm.generate(
            f"Summarize these results: {results}",
            system="Be concise and actionable."
        )
        return summary

### 3.3 Docs/RAG Pipeline

Knowledge base for policy questions: “What is leave policy?”, “How many casual leaves?”

Step 1 — Document Ingestion (One-time setup):

Upload these PDFs/documents:

- Leave Policy (casual, sick, comp-off rules)

- WFH Policy (eligibility, max days)

- Employee Handbook (code of conduct, benefits)

- Holiday Calendar (public + optional holidays)

Step 2 — Chunking & Embedding:

Document: "Casual leave rules: 12 per year, carry 5 forward, no comp off"

Break into chunks (512 tokens each):
  Chunk 1: "Casual leave: 12 per year"
  Chunk 2: "Carry forward: Up to 5 days"
  Chunk 3: "Comp off: Not applicable for casual leaves"

Embed each (text-embedding-3-small) → 1536-dim vector

Store in pgvector:
  INSERT INTO knowledge_embeddings (document_id, chunk_text, embedding)
  VALUES (doc_123, "Casual leave: 12 per year", [0.12, -0.45, ...])

Step 3 — Query Time:

User: "How many casual leaves do I get?"

Embed question: "casual leaves" → [0.13, -0.44, ...]

pgvector similarity search:
  SELECT chunk_text, similarity
  FROM knowledge_embeddings
  WHERE document_id = leave_policy_doc
  ORDER BY embedding <-> query_embedding
  LIMIT 5

Results (top 5 chunks):
  1. "Casual leave: 12 per year" (similarity: 0.95)
  2. "Carry forward: Up to 5 days" (0.87)
  3. "Earned by: 1 per month" (0.82)
  ... etc

LLM answers using only these chunks:
"You get 12 casual leaves per year. You can carry forward up to 5 days to the next year. Earned at 1 per month."

Step 4 — Citation:

Always include source:

"According to Leave Policy v2.1: You get 12 casual leaves per year."
[Source: Leave Policy, Section 3.1]

### 3.4 Database Tables for RAG

CREATE TABLE knowledge_documents (
  id UUID PRIMARY KEY,
  filename VARCHAR(255),
  document_type VARCHAR(50), -- 'policy', 'handbook', 'calendar'
  version VARCHAR(20),
  uploaded_at TIMESTAMP,
  indexed_at TIMESTAMP,
  chunk_count INT
);

CREATE TABLE knowledge_embeddings (
  id UUID PRIMARY KEY,
  document_id UUID REFERENCES knowledge_documents(id),
  chunk_index INT,
  chunk_text TEXT,
  embedding vector(1536), -- pgvector extension required
  created_at TIMESTAMP
);

CREATE INDEX ON knowledge_embeddings USING ivfflat (embedding vector_cosine_ops);

### 3.5 Complex Multi-Step Example: “Pending Approvals with Context”

User: "Show me all pending requests I need to approve, with policy context"

Plan:
  1. Query all pending requests
  2. Get policy info for each request type
  3. Show with context

Step 1 (SQL):
  SELECT * FROM requests WHERE status='pending' AND organization_id='org_1'
  Results: 5 leaves, 2 WFH, 1 comp-off

Step 2 (Docs):
  For leave: Get "Leave Policy" chunk about approval process
  For WFH: Get "WFH Policy" chunk about eligibility
  For comp-off: Get relevant policy chunk

Step 3 (Summarize & Display):
  Card showing:
    5 LEAVE REQUESTS
      - Shlok: April 25-28 (within policy ✓)
      - Saif: April 30 (note: near month-end)
      - Yash: May 1 (next month)
      [Policy: Max 5 consecutive, 12/year limit]
      [Action: Approve | Reject]

    2 WFH REQUESTS
      - Shlok: April 24 (within monthly limit ✓)
      - Saif: April 25
      [Policy: Max 2 WFH per week, employee eligible]
      [Action: Approve | Reject]

    1 COMP-OFF REQUEST
      - Yash: May 2
      [Policy: Only for weekend work, requires manager note]
      [Action: Approve | Reject]

### Testing for Phase 3

- ☐ Multi-step planner creates logical steps

- ☐ Each step executes in order

- ☐ Chat shows progress for each step

- ☐ SQL + Actions combine correctly

- ☐ “Show team progress” returns table with correct data

- ☐ “Pending approvals with policy” shows all requests with context

- ☐ Documents ingested into pgvector

- ☐ “What is leave policy?” answered from docs

- ☐ “How many leaves?” returns correct number

- ☐ Citations show document source

- ☐ Employee sees only their requests

- ☐ Admin sees all requests

### Go/No-Go for Phase 3

✅ “Who’s on HRMS Backend team? Show progress” → Works with multi-step ✅ “Show pending approvals with policy context” → Works ✅ “What is WFH policy?” → Answered from docs with citation ✅ Complex queries complete in <5 seconds ✅ All data filtered by role (no permission leaks)

## Phase 4: Calendar & Email Integration

Duration: 5 days Difficulty: ⭐⭐⭐⭐ (Hard) Deliverable: Email + calendar workflows fully operational

### 4.1 Email Handler

#### Setup (Gmail MCP - Recommended)

Uses existing Gmail integration from your MCP connectors.

class EmailHandler:
    def send_email(self, to: list[str], subject: str, body: str, cc=None):
        """
        to: ["emp1@co.com", "emp2@co.com"]
        subject: "Reminder: You are on leave"
        body: "Dear Shlok,\nThis is a reminder that you are on leave..."
        """
        result = gmail_mcp.send(
            recipients=to,
            subject=subject,
            body=body,
            cc=cc
        )
        log_email(to, subject, result)
        return result
  
    def draft_email(self, context: dict):
        """
        LLM drafts the email body given context
        context: {
            "recipient_name": "Shlok",
            "recipient_email": "shlok@co.com",
            "reason": "on leave",
            "dates": "April 25-28",
            "policy_link": "..."
        }
        """
        prompt = f"""
        Draft a professional reminder email to {context['recipient_name']}
        who is {context['reason']} from {context['dates']}.
        Keep it under 100 words and friendly.
        """
        body = llm.generate(prompt)
        return body

#### Multi-Step Email Workflow: “Find all on-leave employees and send them a reminder”

Step 1 (SQL):
  SELECT e.name, e.email
  FROM employees e
  JOIN requests r ON e.id = r.employee_id
  WHERE r.request_type = 'leave'
  AND r.status = 'approved'
  AND r.date_from <= TODAY()
  AND r.date_to >= TODAY()
  Result: [Shlok, Saif, Yash]

Step 2 (Confirm):
  Chat shows:
  "Found 3 employees on leave today:
   - Shlok (until April 28)
   - Saif (until April 26)
   - Yash (until May 2)
   
   I can send them a reminder email. Proceed? [Yes] [No]"

Step 3 (Draft email - LLM):
  LLM writes:
  "Subject: Reminder - You're on approved leave
   Body: Hi Shlok, This is a friendly reminder that you have approved leave from April 25-28. If this is a mistake, please contact HR. Policy reference: [link]"

Step 4 (Show draft - Chat):
  "Here's the email I'll send. OK to send? [Approve] [Edit] [Cancel]"

Step 5 (Send - Email handler):
  For each: email_handler.send_email(
    to=["shlok@...", "saif@...", "yash@..."],
    subject="Reminder - You're on approved leave",
    body="..."
  )

Step 6 (Report - Chat):
  "✅ Sent reminders to 3 employees:
   - shlok@company.com
   - saif@company.com
   - yash@company.com
   All logged to audit trail."

### 4.2 Calendar Handler

#### Reading Calendar (From your DB)

class CalendarHandler:
    def get_team_availability(self, date: str, project: str):
        """
        Query employees on a project + check their leave for that date
        Returns: {
            available: [emp1, emp2, emp3],
            on_leave: [emp4, emp5],
            wfh: [emp6]
        }
        """
        team = sql_handler.execute(
            f"SELECT employee FROM projects WHERE name='{project}'"
        )
      
        for emp in team:
            # Check if on leave that date
            leave = db.query(
                f"SELECT * FROM requests WHERE employee={emp} AND date={date} AND status='approved'"
            )
            if leave:
                availability['on_leave'].append(emp)
            else:
                availability['available'].append(emp)
      
        return availability

#### Writing to Google Calendar

class CalendarHandler:
    def create_event(self, title: str, date: str, time_from: str, time_to: str, 
                    attendees: list[str], description: str):
        """
        Creates event on Google Calendar
        Sends invites to all attendees
        """
        event = {
            "summary": title,
            "description": description,
            "start": {"dateTime": f"{date}T{time_from}:00"},
            "end": {"dateTime": f"{date}T{time_to}:00"},
            "attendees": [{"email": e} for e in attendees]
        }
      
        result = google_calendar_mcp.create_event(event)
      
        # Log to calendar_events table
        log_calendar_event(result)
      
        return result

#### Multi-Step Calendar Workflow: “Schedule a meeting with AI team Wednesday at 2 PM”

Step 1 (Plan):
  "I need to:
   1. Find AI team members
   2. Check their availability Wednesday
   3. Create calendar event"

Step 2 (SQL - Get team):
  SELECT employee FROM project_assignments
  WHERE project = 'AI Engineering'
  Result: [Yash, Shlok, Saif]

Step 3 (Check availability):
  For each employee on Wednesday:
    - Yash: Available
    - Shlok: On WFH, available
    - Saif: On leave, NOT available

Step 4 (Confirm):
  "Found AI team. Wednesday 2 PM:
   - Yash: ✅ Available
   - Shlok: ✅ Available (WFH)
   - Saif: ❌ On leave
   
   Create meeting with Yash + Shlok? [Yes] [No]"

Step 5 (Create event):
  calendar_handler.create_event(
    title="AI Team Sync",
    date="2026-04-30",
    time_from="14:00",
    time_to="15:00",
    attendees=["yash@...", "shlok@..."],
    description="Discussion: AI roadmap, blockers, next steps"
  )

Step 6 (Report):
  "✅ Meeting created: AI Team Sync, Wednesday 2-3 PM
   Invites sent to: Yash, Shlok
   Note: Saif is on leave, not invited"

### 4.3 Database Tables for Calendar/Email

CREATE TABLE email_log (
  id UUID PRIMARY KEY,
  sent_by UUID REFERENCES employees(id),
  recipients TEXT[], -- emails
  subject VARCHAR(255),
  body TEXT,
  ai_generated BOOLEAN,
  status VARCHAR(20), -- 'sent', 'failed', 'bounced'
  created_at TIMESTAMP,
  sent_at TIMESTAMP
);

CREATE TABLE calendar_events (
  id UUID PRIMARY KEY,
  created_by UUID REFERENCES employees(id),
  title VARCHAR(255),
  description TEXT,
  event_date DATE,
  time_from TIME,
  time_to TIME,
  attendees TEXT[],
  google_calendar_id VARCHAR(255),
  status VARCHAR(20), -- 'created', 'updated', 'cancelled'
  created_at TIMESTAMP
);

### 4.4 Error Handling

Email failures:

If SMTP connection fails:
  - Retry 3 times with exponential backoff
  - Log failed attempt to email_log with status='failed'
  - Show user: "Email to Shlok failed. Retry? [Retry] [Skip]"

If one email fails in batch:
  - Continue sending to others
  - Report: "Sent to 2/3. Failed: saif@company.com (invalid address)"

Calendar failures:

If Google Calendar API fails:
  - Show user: "Calendar integration unavailable. Try again later."
  - Store event in pending_calendar_events table
  - Background job retries every 1 hour

If attendee email invalid:
  - Skip that attendee
  - Report: "Created event, but couldn't invite yash (invalid email)"

### Testing for Phase 4

- ☐ “Send email to Shlok” works end-to-end

- ☐ “Find on-leave employees and email them” sends to right people

- ☐ Email shows in Gmail

- ☐ Email logged to email_log table

- ☐ “Create calendar event with AI team” creates on Google Calendar

- ☐ Invites sent to attendees

- ☐ “Schedule meeting when team is available” checks availability correctly

- ☐ Handles failures gracefully (SMTP down, API error)

- ☐ Batch operations work (email 50+ people in <10 seconds)

- ☐ All actions require confirmation before executing

### Go/No-Go for Phase 4

✅ Admins can send bulk emails to filtered groups ✅ Calendar events created on Google Calendar ✅ Meeting scheduling checks team availability ✅ All workflows logged (audit trail complete) ✅ Errors handled gracefully without data loss

## Database Schema

### Complete Schema Overview

-- Existing tables (you have these)
-- employees, attendance_sessions, requests, projects, tasks, leaves, etc.

-- NEW tables for AI system
CREATE TABLE ai_conversations (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  employee_id UUID NOT NULL REFERENCES employees(id) ON DELETE CASCADE,
  organization_id UUID NOT NULL,
  message_role VARCHAR(20) NOT NULL, -- 'user' or 'assistant'
  message_content TEXT NOT NULL,
  turn_number INT NOT NULL, -- which turn in conversation
  created_at TIMESTAMP NOT NULL DEFAULT CURRENT_TIMESTAMP,
  
  INDEX idx_employee_org (employee_id, organization_id),
  INDEX idx_created_at (created_at)
);

CREATE TABLE ai_audit_log (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  employee_id UUID NOT NULL REFERENCES employees(id),
  organization_id UUID NOT NULL,
  intent_type VARCHAR(50) NOT NULL, -- ACTION, SQL, DOCS, MULTI_STEP
  action_taken VARCHAR(255),
  api_called VARCHAR(255),
  parameters JSONB,
  result VARCHAR(50), -- 'success', 'failed', 'error'
  error_message TEXT,
  llm_confidence FLOAT,
  response_time_ms INT,
  created_at TIMESTAMP NOT NULL DEFAULT CURRENT_TIMESTAMP,
  
  INDEX idx_employee (employee_id),
  INDEX idx_action (action_taken),
  INDEX idx_created_at (created_at)
);

CREATE TABLE knowledge_documents (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  organization_id UUID NOT NULL,
  filename VARCHAR(255) NOT NULL,
  document_type VARCHAR(50), -- 'policy', 'handbook', 'calendar'
  version VARCHAR(20),
  uploaded_at TIMESTAMP NOT NULL DEFAULT CURRENT_TIMESTAMP,
  indexed_at TIMESTAMP,
  chunk_count INT DEFAULT 0,
  
  UNIQUE(organization_id, filename)
);

CREATE TABLE knowledge_embeddings (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  document_id UUID NOT NULL REFERENCES knowledge_documents(id) ON DELETE CASCADE,
  organization_id UUID NOT NULL,
  chunk_index INT NOT NULL,
  chunk_text TEXT NOT NULL,
  embedding vector(1536), -- Requires pgvector extension
  created_at TIMESTAMP NOT NULL DEFAULT CURRENT_TIMESTAMP,
  
  INDEX idx_document (document_id),
  INDEX idx_embedding ON knowledge_embeddings USING ivfflat (embedding vector_cosine_ops)
);

CREATE TABLE email_log (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  sent_by UUID NOT NULL REFERENCES employees(id),
  organization_id UUID NOT NULL,
  recipients TEXT[] NOT NULL,
  subject VARCHAR(255) NOT NULL,
  body TEXT,
  ai_generated BOOLEAN DEFAULT false,
  status VARCHAR(20) DEFAULT 'pending', -- 'pending', 'sent', 'failed', 'bounced'
  error_message TEXT,
  created_at TIMESTAMP NOT NULL DEFAULT CURRENT_TIMESTAMP,
  sent_at TIMESTAMP,
  
  INDEX idx_sent_by (sent_by),
  INDEX idx_status (status),
  INDEX idx_created_at (created_at)
);

CREATE TABLE calendar_events (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  created_by UUID NOT NULL REFERENCES employees(id),
  organization_id UUID NOT NULL,
  title VARCHAR(255) NOT NULL,
  description TEXT,
  event_date DATE NOT NULL,
  time_from TIME NOT NULL,
  time_to TIME NOT NULL,
  attendees TEXT[] NOT NULL,
  google_calendar_id VARCHAR(255),
  status VARCHAR(20) DEFAULT 'created', -- 'created', 'updated', 'cancelled'
  created_at TIMESTAMP NOT NULL DEFAULT CURRENT_TIMESTAMP,
  
  INDEX idx_created_by (created_by),
  INDEX idx_event_date (event_date),
  INDEX idx_created_at (created_at)
);

## Security & RBAC

### Role-Based Access Control

All handlers enforce role checks before executing:

Employee Role:

- Can check-in/out (own only)

- Can apply leave (own only)

- Can view own tasks, balance, requests

- Cannot approve others’ requests

- Cannot view other employees’ data

- Cannot add/deactivate employees

- Cannot send bulk emails

Admin Role:

- Can check-in/out (own or on behalf of others)

- Can apply/approve/reject any leave request

- Can view all employees’ data

- Can add/deactivate employees

- Can create holidays, projects

- Can send bulk emails

- Can run reports

- Cannot access payroll data

### Query-Level RBAC

Every SQL query adds a WHERE clause:

-- Employee query (filtered automatically)
SELECT * FROM attendance_sessions
WHERE employee_id = [CURRENT_USER_ID]

-- Admin query (full access)
SELECT * FROM attendance_sessions
WHERE organization_id = [ORG_ID]

### API-Level Security

def check_permission(user_role: str, required_role: str) -> bool:
    """
    Enforce role requirements on every action
    """
    if required_role == "employee" and user_role in ["employee", "admin"]:
        return True
    if required_role == "admin" and user_role == "admin":
        return True
    return False

# Usage in handler
def action_approve_leave(request_id: str, user: User):
    if not check_permission(user.role, "admin"):
        raise PermissionError("Only admins can approve leave")
  
    # Proceed with approval
    ...

### Audit Trail

Every action logged with:

- WHO (employee_id)

- WHAT (action_taken)

- WHEN (timestamp)

- RESULT (success/failure)

- PARAMETERS (what was changed)

No action is “invisible.”

### LLM Safety

- Classify user messages for prompt injection attempts

- Reject suspicious patterns

- Never expose raw DB schema or table names to LLM

- Always parameterize queries (no string interpolation)

- Rate limit: 60 requests/user/hour to prevent abuse

## Appendix A: Glossary

- Intent: User message classification (ACTION, SQL, DOCS, etc.)

- Handler: Component that executes a specific intent type

- RBAC: Role-Based Access Control (employee vs admin)

- RAG: Retrieval-Augmented Generation (query documents for answers)

- pgvector: PostgreSQL extension for vector similarity search

- Audit Log: Immutable record of every AI action

- Planner: Multi-step orchestrator that breaks complex queries into steps

- Template: Pre-written SQL query with parameterized values

- Confidence: LLM’s own assessment of how sure it is (0-1)

## Appendix B: File Structure

backend/app/
├── ai/
│   ├── __init__.py
│   ├── router.py                    ← POST /ai/chat endpoint
│   ├── classifier.py                ← Intent classification
│   ├── context.py                   ← User context builder
│   ├── history.py                   ← Conversation history
│   │
│   ├── handlers/
│   │   ├── __init__.py
│   │   ├── action_handler.py        ← API calls
│   │   ├── sql_handler.py           ← Query execution
│   │   ├── docs_handler.py          ← RAG pipeline
│   │   ├── email_handler.py         ← Email sending
│   │   ├── calendar_handler.py      ← Calendar events
│   │   └── planner.py               ← Multi-step orchestrator
│   │
│   ├── sql/
│   │   ├── templates.py             ← SQL query templates
│   │   ├── validator.py             ← Query safety checks
│   │   └── executor.py              ← Execute with params
│   │
│   ├── knowledge/
│   │   ├── ingestion.py             ← Document upload + chunk
│   │   ├── embeddings.py            ← Generate embeddings
│   │   ├── retriever.py             ← Vector search
│   │   └── rag_chain.py             ← Full RAG pipeline
│   │
│   └── models.py                    ← DB models

frontend/src/components/ai/
├── AIChatButton.tsx
├── AIChatPanel.tsx
├── AIChatMessage.tsx
├── AIChatInput.tsx
├── AIChatQuickActions.tsx
├── ConfirmDialog.tsx
├── StatusCard.tsx
└── useAIChat.ts                     ← Hook for API calls

database/migrations/
├── 001_ai_conversations.sql
├── 002_ai_audit_log.sql
├── 003_knowledge_documents.sql
├── 004_knowledge_embeddings.sql
├── 005_email_log.sql
└── 006_calendar_events.sql

## Appendix C: Key Environment Variables

# LLM Configuration
ANTHROPIC_API_KEY=sk-ant-...
LLM_DEFAULT_MODEL=claude-sonnet-4-20250514
LLM_FAST_MODEL=claude-haiku-4-5-20251001

# Database
DATABASE_URL=postgresql://user:pass@localhost/hrms_db
SUPABASE_URL=https://xxxx.supabase.co
SUPABASE_KEY=...

# Email
GMAIL_API_KEY=... (if using Gmail MCP)
SMTP_HOST=smtp.gmail.com
SMTP_PORT=587
SMTP_USER=noreply@company.com
SMTP_PASS=...

# Calendar
GOOGLE_CALENDAR_API_KEY=...

# Security
JWT_SECRET=your-secret-key
RATE_LIMIT_REQUESTS=60
RATE_LIMIT_WINDOW=3600

# Feature Flags
ENABLE_AI_CHAT=true
ENABLE_SQL_QUERIES=true
ENABLE_MULTI_STEP=true
ENABLE_EMAIL=false  # Phase 4 only
ENABLE_CALENDAR=false  # Phase 4 only

Document Complete Last Updated: April 2026 Next Review: Upon Phase 1 completion